## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 1 | Login (Admin) | Failed login with correct username and correct password. Redirected page does not exist. | High | 5 | 20 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
2 | 1 | Login (Admin) | Failed login with correct username and wrong password. Did not redirect back to login.php | High | 5
3 | 1 | Login (Admin) | Failed login with correct username and wrong password. Error with StudentDAO. | High | 5
4 | 1 | Login (Admin) | Failed login with correct username and correct password. Admin_homepage is blank. | High | 5
5 | 1 | Bootstrap | Failed bootstrap. One of the files is empty. | Critical | 10 | 41 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
6 | 1 | Bootstrap | Failed bootstrap. Error 500 when using removeAll() due to foreign key constraint. | High | 5
7 | 1 | Bootstrap | Failed bootstrap. No defined method $coursedao->retrieveAllByCourse(). | High | 5
8 | 1 | Bootstrap | Failed bootstrap. Error processing errors due to strlen($errors) | High | 5
9 | 1 | Bootstrap | Failed bootstrap. Correct lines are rejected and considered an error when processing bid.csv | High | 5
10 | 1 | Bootstrap | Failed bootstrap. Cannot insert lines in many .csv files into database due to improper parameter binding. | High | 5
11 | 1 | Bootstrap | Failed bootstrap. Cannot insert lines for bid.csv into database due to names are considered invalid. | High | 5
12 | 1 | Bootstrap | Wrong message is displayed to inform admin of missing/wrong files when bootstrapping files. | Low | 1
13 | 2 | Bootstrap | Student Class lack one closing bracket | High | 5 | 159 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
14 | 2 | Bootstrap | Incorrect num-record-loaded, show all 0 | Low | 1
15 | 2 | Bootstrap | StudentDAO: Fatal error: UncaughtPDOException, wrong name specified for e$ column | Low | 1
16 | 2 | Clearing logic | Out of range value for minimum bid | High | 5
17 | 2 | Bootstrap | Permission denied when trying to write to file | High | 5
18 | 2 | Clearing Logic | System does not register invalid courses and invalid sections(send user straight to bid processing page) | High | 5
19 | 2 | Bootstrap | Array to string conversion error. Error messages in each line are still in the array | Critical | 10
20 | 2 | Bootstrap | Each bid failed with 'not own school course' error | Critical | 10
21 | 2 | Bootstrap | Undefined index when retrieving bid section by status | Critical | 10
22 | 2 | Clearing Logic | Uncaught Error: Call to a member function getVacancy() on string | High | 5
23 | 2 | Clearing Logic | count() error: Parameter is not a countable variable | High | 5
24 | 2 | Clearing Logic | Uncaught PDOException: SQLSTATE[42S22]: Column 'course' not found in 'where clause' | High | 5
25 | 2 | Clearing Logic | Fatal error: Uncaught PDOException: SQLSTATE[HY093]: Parameter $amount is not identified | Critical | 10
26 | 2 | Clearing Logic | Fatal error: Uncaught Error: Call to a member function getVacancyDrop() | Critical | 10
27 | 2 | Clearing Logic | Fatal error: Uncaught Error: Call to a member function getEdollar() | Critical | 10
28 | 2 | Adding Bids | Fatal error: Uncaught PDOException: SQLSTATE[23000]: Integrity constraint violation: 1062 Duplicate entry 'ben.ng.2009-IS100' for key 'PRIMARY' | High | 5
29 | 2 | Adding Bids | PDOException: SQLSTATE[42S22]: Column not found: 1054 Unknown column 'round' in 'field list' | High | 5
30 | 2 | Adding Bids | Undefined function retrieveSectionByCourse() | High | 5
31 | 2 | Adding Bids | undefined method BidDAO::retrieveBiddedSectionsByStatus() | High | 5
32 | 2 | Bootstrap | Row number not corresponding to excel by 1 | Low | 1
33 | 2 | Bootstrap | PDOException: SQLSTATE[23000]: Integrity constraint violation: 1062 Duplicate entry 'IS100' for key 'PRIMARY' for test file 006-bootstrap | High | 5
34 | 2 | Bootstrap | Protect JSON not working for Bootstrap and Web API | Critical | 10
35 | 2 | Bootstrap | System does not recognize wrong token in 017-bootstrap | Critical | 10
36 | 2 | Bootstrap | number not showing inside JSON for all csv files in 010-bootstrap | Critical | 10
37 | 3 | Delete Bid | Bid not deleted after deleting it through Web API | High | 5 | 169 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
38 | 3 | Add Bid Form | Error message does not show when an unsuccessful bid is made | High | 5
39 | 3 | Update/Add Bid | After adding a bid, e$ is not deducted from the student | High | 5
40 | 3 | Update/Add Bid | When the student updates a failed bid in Round 2, validation is unable to check if they have enough e$ | High | 5
41 | 3 | Student Home Page | Unable to display student's id in the welcome message | Low | 1
42 | 3 | Drop Section | Errors could not be displayed due to a array to string error | Critical | 10
43 | 3 | Delete Bid | Errors could not be displayed due to a array to string error | Critical | 10
44 | 3 | Update/Add Bid | Errors could not be displayed due to a array to string error | Critical | 10
45 | 3 | Update/Add Bid | Wrong error message is displayed when updating/adding bids | Low | 1
46 | 3 | Authenticate | Unable to authenticate when the user (student and admin) logins | High | 10
47 | 3 | Delete Bid | Fixed a bug where user cannot delete bid made during bootstrap because of triggering "no such bid" and "invalid userid". | Critical | 10
48 | 3 | Login | Protect.php kicks in even though correct login information is entered | High | 5
49 | 3 | Bootstrap | Round number for bootstrapped bids is incorrect | Low | 1
50 | 3 | Add Bid Form | Add Bid Form unable to send userid stored in session to the UpdateBid function | Critical | 10
51 | 3 | Update/Add Bid | Add Bid does not update the section with the correct Min Bid | High | 5
52 | 3 | User-Dump | Unable to verify token when token is not passed through URL. | Critical | 10
53 | 3 | Round 2 Clearing | Unable to calculate the correct clearing price when a new bid is added. | Critical | 10
54 | 3 | Bootstrap | Validation within bootstrap redirects user to the admin_homepage instead of displaying error | Critical | 10
55 | 3 | Round 2 Clearing | Round 2 Clearing does not reflect the correct number of vacancies in the section. | High | 5
56 | 3 | Round 2 Clearing | Round 2 Clearing causes all bids to be successful, even when some shouldn't. | High | 5
57 | 3 | - | Unnecessary parameter binded in SectionDAO when retrieving all sections. | Low | 1
58 | 3 | Drop Section | Drop section failed due to userid of student not being found | Critical | 10
59 | 3 | Drop Section | Included increasing the vacancy when students drops a bid for section | High | 5
60 | 3 | Update/Add Bid | Update/Add Bid does not check if student has enough e$ during Round 2 | High | 5
61 | 3 | Update/Add Bid | Update/Add Bid does not check if student has exceeded the number of sections that he can bid for | High | 5
62 | 3 | Add Bid Form | Update/Add Bid does not work if the amount is an integer | Critical | 10
63 | 4 | Authenticate | JSON yours 000-authenticate error message displayed "messages" instead of "message" | Low | 1 | 67 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
64 | 4 | Bootstrap | JSON bootstrap preg_match for exam_start and exam_end for the second digit range was from 1-9 instead of 0-9 | High | 5
65 | 4 | Bootstrap | JSON bootstrap preg_match for exam_start time is after exam_ end time | High | 5
66 | 4 | Bootstrap | JSON checker error message column "line" instead of "row" | Low | 1
67 | 4 | Bootstrap | JSON checker error message "insufficient e$" instead of "not enough e-dollar" | Low | 1
68 | 4 | Bootstrap | JSON checker "num-record-loaded" for bid.csv is 1 instead of 4 | High | 5
69 | 4 | Admin homepage | error message should be "line" instead of "row" | Low | 1
70 | 4 | Add bid | $_SESSION['errors'] = $result['message']; instead of $_SESSION['errors'] = $result['messages']; | Low | 1
71 | 4 | Delete bid | $_SESSION['errors'] = $result['message']; instead of $_SESSION['errors'] = $result['messages']; | Low | 1
72 | 4 | Drop Section | $_SESSION['errors'] = $result['message']; instead of $_SESSION['errors'] = $result['messages']; | Low | 1
73 | 4 | Drop Section | $errors[] = "round not active"; instead of $errors[] = "round ended"; | Low | 1
74 | 4 | Update bid | "message" => $errors instead of "messages" => $errors | Low | 1
75 | 4 | Authenticate | "message" => array_values($errors) instead of "messages" => array_values($errors) | Low | 1
76 | 4 | JSON dump | "message" => array_values($errors) instead of "messages" => array_values($errors) | Low | 1
77 | 4 | SQL database | school` varchar(128) instead of school` varchar(4) | Critical | 10
78 | 4 | Round clearing | Incorrect vacancies in round 2 clearing logic | Critical | 10
79 | 4 | Bootstrap | Incorrect exam date not flagged out in validation | High | 5
80 | 4 | Bootstrap | extra space ' ' in string. $row_errors[] = "invalid e-dollar"; instead of $row_errors[] = "invalid e-dollar"; | Low | 1
81 | 4 | Bootstrap | Incorrect number for total bids validated | High | 5
82 | 4 | Bootstrap | Invalid bidding amount less than $10 not flagged out | High | 5
83 | 4 | Bootstrap | Errors in exam timetable clashes | High | 5
84 | 4 | Bid dump | Although the bid amount was sufficient and the bid made in round 2 is successful, as round 2 has not ended, bid result should be "-" instead of "in". | High | 5
85 | 4 | Section dump | Section-dump should only retrieve results of previous rounds. However, current rounds are included. | High | 5
86 | 5 | Bootstrap | If the number of sections bidded for is 6, section limit reached error message is not shown. | High | 5 | 15 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
87 | 5 | Round 2 Clearing | Incorrect min bid value is reflected for the section unless the user drops the bid and re-bids. | Critical | 10
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198

## Bug Log
Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team)
1 | 1 | Login (Admin) | Failed login with correct username and correct password. Redirected page does not exist. | Resolved | 2019-09-28 | 2019-09-28 | RL & NTM
2 | 1 | Login (Admin) | Failed login with correct username and wrong password. Did not redirect back to login.php | Resolved | 2019-09-28 | 2019-09-28 | RL & NTM
3 | 1 | Login (Admin) | Failed login with correct username and wrong password. Error with StudentDAO. | Resolved | 2019-09-28 | 2019-09-28 | RL & NTM
4 | 1 | Login (Admin) | Failed login with correct username and correct password. Admin_homepage is blank. | Resolved | 2019-09-28 | 2019-09-28 | RL & NTM
5 | 1 | Bootstrap | Failed bootstrap. One of the files is empty. | Resolved | 2019-09-28 | 2019-09-28 | CWHE,WP & FT
6 | 1 | Bootstrap | Failed bootstrap. Error 500 when using removeAll() due to foreign key constraint. | Resolved | 2019-09-28 | 2019-09-28 | CWHE,WP & FT
7 | 1 | Bootstrap | Failed bootstrap. No defined method $coursedao->retrieveAllByCourse(). | Resolved | 2019-09-28 | 2019-09-28 | CWHE,WP & FT
8 | 1 | Bootstrap | Failed bootstrap. Error processing errors due to strlen($errors) | Resolved | 2019-09-28 | 2019-09-28 | CWHE,WP & FT
9 | 1 | Bootstrap | Failed bootstrap. Correct lines are rejected and considered an error when processing bid.csv | Resolved | 2019-09-28 | 2019-09-28 | CWHE,WP & FT
9 | 1 | Bootstrap | Failed bootstrap. Cannot insert lines in many .csv files into database due to improper parameter binding. | Resolved | 2019-09-28 | 2019-09-28 | CWHE,WP & FT
10 | 1 | Bootstrap | Failed bootstrap. Cannot insert lines for bid.csv into database due to names are considered invalid. | Resolved | 2019-09-28 | 2019-09-28 | CWHE,WP & FT
11 | 1 | Bootstrap | Wrong message is displayed to inform admin of missing/wrong files when bootstrapping files. | Resolved | 2019-09-28 | 2019-09-28 | CWHE & FT
13 | 2 | Bootstrap | Student Class lack one closing bracket | Resolved | 2019-10-06 | 2019-10-06 | NTM,CWHE & WP
14 | 2 | Bootstrap | Incorrect num-record-loaded, show all 0 | Resolved | 2019-10-06 | 2019-10-06 | NTM,CWHE & WP
15 | 2 | Bootstrap | StudentDAO: Fatal error: UncaughtPDOException, wrong name specified for e$ column | Resolved | 2019-10-06 | 2019-10-06 | NTM,CWHE & WP
16 | 2 | Clearing logic | Out of range value for minimum bid | Resolved | 2019-10-06 | 2019-10-10 | RL & FT
17 | 2 | Bootstrap | Permission denied when trying to write to file | Resolved | 2019-10-06 | 2019-10-09 | RL & FT
18 | 2 | Clearing Logic | System does not register invalid courses and invalid sections(send user straight to bid processing page) | Resolved | 2019-10-06 | 2019-10-09 | RL & FT
19 | 2 | Bootstrap | Array to string conversion error. Error messages in each line are still in the array | Resolved | 2019-10-06 | 2019-10-09 | RL & FT
20 | 2 | Bootstrap | Each bid failed with 'not own school course' error | Resolved | 2019-10-06 | 2019-10-09 | RL & FT
21 | 2 | Bootstrap | Undefined index when retrieving bid section by status | Resolved | 2019-10-06 | 2019-10-09 | RL & FT
22 | 2 | Clearing Logic | Uncaught Error: Call to a member function getVacancy() on string | Resolved | 2019-10-06 | 2019-10-13 | RL & FT
23 | 2 | Clearing Logic | count() error: Parameter is not a countable variable | Resolved | 2019-10-10 | 2019-10-13 | RL & FT
24 | 2 | Clearing Logic | Uncaught PDOException: SQLSTATE[42S22]: Column 'course' not found in 'where clause' | Resolved | 2019-10-10 | 2019-10-13 | CWHE & WP
25 | 2 | Clearing Logic | Fatal error: Uncaught PDOException: SQLSTATE[HY093]: Parameter $amount is not identified | Resolved | 2019-10-10 | 2019-10-13 | CWHE & WP
26 | 2 | Clearing Logic | Fatal error: Uncaught Error: Call to a member function getVacancyDrop() | Resolved | 2019-10-10 | 2019-10-13 | CWHE & WP
27 | 2 | Clearing Logic | Fatal error: Uncaught Error: Call to a member function getEdollar() | Resolved | 2019-10-12 | 2019-10-13 | CWHE & WP
28 | 2 | Adding Bids | Fatal error: Uncaught PDOException: SQLSTATE[23000]: Integrity constraint violation: 1062 Duplicate entry 'ben.ng.2009-IS100' for key 'PRIMARY' | Resolved | 2019-10-12 | 2019-10-13 | CWHE & WP
29 | 2 | Adding Bids | PDOException: SQLSTATE[42S22]: Column not found: 1054 Unknown column 'round' in 'field list' | Resolved | 2019-10-12 | 2019-10-13 | CWHE & WP
30 | 2 | Adding Bids | Undefined function retrieveSectionByCourse() | Resolved | 2019-10-12 | 2019-10-13 | CWHE & WP
31 | 2 | Adding Bids | undefined method BidDAO::retrieveBiddedSectionsByStatus() | Resolved | 2019-10-12 | 2019-10-13 | NTM,FT & RL
32 | 2 | Bootstrap | Row number not corresponding to excel by 1 | Resolved | 2019-10-12 | 26/10/2019 | FT & NTM
33 | 2 | Bootstrap | PDOException: SQLSTATE[23000]: Integrity constraint violation: 1062 Duplicate entry 'IS100' for key 'PRIMARY' for test file 006-bootstrap | Resolved | 2019-10-12 | 2019-10-13 | NTM,FT & RL
34 | 2 | Bootstrap | Protect JSON not working for Bootstrap and Web API | Resolved | 2019-10-14 | 1900-10-14 | CWHE & WP
35 | 2 | Bootstrap | System does not recognize wrong token in 017-bootstrap | Resolved | 2019-10-13 | 2019-10-13 | CWHE & WP
36 | 2 | Bootstrap | number not showing inside JSON for all csv files in 010-bootstrap | Resolved | 2019-10-13 | 2019-10-13 | RL & FT
37 | 3 | Delete Bid | Bid not deleted after deleting it through Web API | Resolved | 21/10/2019 | 21/10/2019 | FT & NTM
38 | 3 | Add Bid Form | Error message does not show when an unsuccessful bid is made | Resolved | 21/10/2019 | 21/10/2019 | FT & NTM
39 | 3 | Update/Add Bid | After adding a bid, e$ is not deducted from the student | Resolved | 21/10/2019 | 21/10/2019 | FT & NTM
40 | 3 | Update/Add Bid | When the student updates a failed bid in Round 2, validation is unable to check if they have enough e$ | Resolved | 21/10/2019 | 21/10/2019 | FT & NTM
41 | 3 | Student Home Page | Unable to display student's id in the welcome message | Resolved | 21/10/2019 | 21/10/2019 | FT & NTM
42 | 3 | Drop Section | Errors could not be displayed due to a array to string error | Resolved | 21/10/2019 | 21/10/2019 | FT & NTM
43 | 3 | Delete Bid | Errors could not be displayed due to a array to string error | Resolved | 21/10/2019 | 21/10/2019 | FT & NTM
44 | 3 | Update/Add Bid | Errors could not be displayed due to a array to string error | Resolved | 21/10/2019 | 21/10/2019 | FT & NTM
45 | 3 | Update/Add Bid | Wrong error message is displayed when updating/adding bids | Resolved | 21/10/2019 | 21/10/2019 | FT & NTM
46 | 3 | Authenticate | Unable to authenticate when the user (student and admin) logins | Resolved | 21/10/2019 | 21/10/2019 | FT & NTM
47 | 3 | Login | Protect.php kicks in even though correct login information is entered | Resolved | 22/10/2019 | 22/10/2019 | FT & NTM
48 | 3 | Delete Bid | Fixed a bug where user cannot delete bid made during bootstrap because of triggering "no such bid" and "invalid userid". | Resolved | 23/10/2019 | 23/10/2019 | CWHE & RL
49 | 3 | Bootstrap | Round number for bootstrapped bids is incorrect | Resolved | 26/10/2019 | 26/10/2019 | CWHE & RL
50 | 3 | Add Bid Form | Add Bid Form unable to send userid stored in session to the UpdateBid function | Resolved | 26/10/2019 | 26/10/2019 | CWHE & RL
51 | 3 | Update/Add Bid | Add Bid does not update the section with the correct Min Bid | Resolved | 26/10/2019 | 26/10/2019 | FT & NTM
52 | 3 | User-Dump | Unable to verify token when token is not passed through URL. | Resolved | 28/10/2019 | 28/10/2019 | CWHE & RL
53 | 3 | Round 2 Clearing | Unable to calculate the correct clearing price when a new bid is added. | Resolved | 28/10/2019 | 28/10/2019 | FT & CWHE
54 | 3 | Bootstrap | Validation within bootstrap redirects user to the admin_homepage instead of displaying error | Resolved | 28/10/2019 | 28/10/2019 | FT & NTM
55 | 3 | Round 2 Clearing | Round 2 Clearing does not reflect the correct number of vacancies in the section. | Resolved | 28/10/2019 | 28/10/2019 | FT & NTM
56 | 3 | Round 2 Clearing | Round 2 Clearing causes all bids to be successful, even when some shouldn't. | Resolved | 28/10/2019 | 28/10/2019 | FT & NTM
57 | 3 | - | Unnecessary parameter binded in SectionDAO when retrieving all sections. | Resolved | 28/10/2019 | 28/10/2019 | CWHE & WP
58 | 3 | Drop Section | Drop section failed due to userid of student not being found | Resolved | 28/10/2019 | 28/10/2019 | CWHE & RL
59 | 3 | Drop Section | Included increasing the vacancy when students drops a bid for section | Resolved | 28/10/2019 | 28/10/2019 | CWHE & RL
60 | 3 | Update/Add Bid | Update/Add Bid does not check if student has enough e$ during Round 2 | Resolved | 28/10/2019 | 28/10/2019 | FT & NTM
61 | 3 | Update/Add Bid | Update/Add Bid does not check if student has exceeded the number of sections that he can bid for | Resolved | 28/10/2019 | 28/10/2019 | FT & NTM
62 | 3 | Add Bid Form | Update/Add Bid does not work if the amount is an integer | Resolved | 28/10/2019 | 28/10/2019 | CWHE & RL
63 | 4 | Authenticate | JSON yours 000-authenticate error message displayed "messages" instead of "message" | Resolved | 2019-11-08 | 2019-11-08 | WP & RL
64 | 4 | Bootstrap | JSON bootstrap preg_match for exam_start and exam_end for the second digit range was from 1-9 instead of 0-9 | Resolved | 2019-11-08 | 2019-11-08 | WP & RL
65 | 4 | Bootstrap | JSON bootstrap preg_match for exam_start time is after exam_ end time | Resolved | 2019-11-08 | 2019-11-08 | WP & RL
66 | 4 | Bootstrap | JSON checker error message column "line" instead of "row" | Resolved | 2019-11-08 | 2019-11-08 | WP & RL
67 | 4 | Bootstrap | JSON checker error message "insufficient e$" instead of "not enough e-dollar" | Resolved | 2019-11-08 | 2019-11-08 | WP & RL
68 | 4 | Bootstrap | JSON checker "num-record-loaded" for bid.csv is 1 instead of 4 | Resolved | 2019-11-08 | 2019-11-08 | WP & RL
69 | 4 | Admin homepage | error message should be "line" instead of "row" | Resolved | 2019-11-08 | 2019-11-08 | WP & RL
70 | 4 | Add bid | $_SESSION['errors'] = $result['message']; instead of $_SESSION['errors'] = $result['messages']; | Resolved | 2019-11-08 | 2019-11-08 | CWHE & NTM
71 | 4 | Delete bid | $_SESSION['errors'] = $result['message']; instead of $_SESSION['errors'] = $result['messages']; | Resolved | 2019-11-08 | 2019-11-08 | CWHE & NTM
72 | 4 | Drop Section | $_SESSION['errors'] = $result['message']; instead of $_SESSION['errors'] = $result['messages']; | Resolved | 2019-11-08 | 2019-11-08 | CWHE & NTM
73 | 4 | Drop Section | $errors[] = "round not active"; instead of $errors[] = "round ended"; | Resolved | 2019-11-08 | 2019-11-08 | CWHE & NTM
74 | 4 | Update bid | "message" => $errors instead of "messages" => $errors | Resolved | 2019-11-08 | 2019-11-08 | CWHE & NTM
75 | 4 | Authenticate | "message" => array_values($errors) instead of "messages" => array_values($errors) | Resolved | 2019-11-08 | 2019-11-12 | WP & RL
76 | 4 | JSON dump | "message" => array_values($errors) instead of "messages" => array_values($errors) | Resolved | 2019-11-08 | 2019-11-12 | WP & RL
77 | 4 | SQL database | school` varchar(128) instead of school` varchar(4) | Resolved | 2019-11-08 | 2019-11-12 | WP & RL
78 | 4 | Round clearing | Incorrect vacancies in round 2 clearing logic | Resolved | 2019-11-08 | 2019-11-15 | CWHE & NTM
79 | 4 | Bootstrap | Incorrect exam date not flagged out in validation | Resolved | 2019-11-08 | 2019-11-15 | CWHE & NTM
80 | 4 | Bootstrap | extra space ' ' in string. $row_errors[] = "invalid e-dollar"; instead of $row_errors[] = "invalid e-dollar"; | Resolved | 2019-11-08 | 2019-11-15 | CWHE & NTM
81 | 4 | Bootstrap | Incorrect number for total bids validated | Resolved | 2019-11-08 | 2019-11-15 | CWHE & NTM
82 | 4 | Bootstrap | Invalid bidding amount less than $10 not flagged out | Resolved | 2019-11-08 | 2019-11-15 | CWHE & NTM
83 | 4 | Bootstrap | Errors in exam timetable clashes | Resolved | 2019-11-08 | 2019-11-15 | CWHE & NTM
84 | 4 | Bid dump | Although the bid amount was sufficient and the bid made in round 2 is successful, as round 2 has not ended, bid result should be "-" instead of "in". | Resolved | 2019-11-08 | 2019-11-15 | CWHE & NTM
85 | 4 | Section dump | Section-dump should only retrieve results of previous rounds. However, current rounds are included. | Resolved | 2019-11-08 | 2019-11-15 | CWHE & NTM
86 | 5 | Bootstrap | If the number of sections bidded for is 6, section limit reached error message is not shown. | Resolved | 2019-11-16 | 2019-11-16 | CWHE & FT
87 | 5 | Round 2 Clearing | Incorrect min bid value is reflected for the section unless the user drops the bid and re-bids. | Resolved | 2019-11-16 | 2019-11-16 | CWHE & FT