## Week 13
| Question | Week 13: 11/11/2019 to 17/11/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Eugene | What did you do yesterday? | UAT JSON Testcases | UAT JSON Testcases | UAT JSON Testcases | Finish up JSON UAT Debug | Filter functions and UI improvements | Integrate UI improvements | Integration and Deployment
| What will you do today? | UAT JSON Debug | UAT JSON Debug | Finish up UAT JSON Debug | Filter functions and UI Improvements | Integrate UI improvements | Integration and Deployment | Integration and Deployment
| Do you have any obstacles? | - | - | - | - | - | - | -
Wang Piao | What did you do yesterday? | UAT JSON Testcases | UAT JSON Testcases | UAT JSON Testcases | Finish up JSON UAT Debug | Finish up JSON UAT Debug | Final Testing | Integration and Deployment
| What will you work on today? | UAT JSON Debug | UAT JSON Debug | Finish up UAT JSON Debug | Finish up JSON UAT Debug | Final Testing | Integration and Deployment | Integration and Deployment
| Do you have any obstacles? | - | - | - | - | - | - | -
Francine | What did you do yesterday? | UAT JSON Testcases | UAT JSON Testcases | UAT JSON Testcases | Finish up JSON UAT Debug | Finish up JSON UAT Debug | Tidy up schedule | Integration and Deployment
| What will you work on today? | UAT JSON Debug | UAT JSON Debug | Finish up UAT JSON Debug | Finish up JSON UAT Debug | Tidy up schedule | Integration and Deployment | Integration and Deployment
| Do you have any obstacles? | - | - | - | - | - | - | -
Risa | What did you do yesterday? | UAT JSON Testcases | UAT JSON Testcases | UAT JSON Testcases | Finish up JSON UAT Debug | Finish up JSON UAT Debug | Final Testing | Integration and Deployment
| What will you work on today? | UAT JSON Debug | UAT JSON Debug | Finish up UAT JSON Debug | Finish up JSON UAT Debug | Final Testing | Integration and Deployment | Integration and Deployment
| Do you have any obstacles? | - | - | - | - | - | - | -
Minh | What did you do yesterday? | UAT JSON Testcases | UAT JSON Testcases | UAT JSON Testcases | Finish up JSON UAT Debug | Filter functions and UI improvements | Integrate UI improvements | Integration and Deployment
| What will you work on today? | UAT JSON Debug | UAT JSON Debug | Finish up UAT JSON Debug | Filter functions and UI Improvements | Integrate UI improvements | Integration and Deployment | Integration and Deployment
| Do you have any obstacles? | - | - | - | - | - | - | -

## Week 12
| Question | Week 12: 4/11/2019 to 10/11/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Eugene | What did you do yesterday? | Debugging bugs caught during UAT | Debugging and the implementation of our additional function | Debugging and the implementation of our additional function | Debugging and the implementation of our additional function | Not a working day | UAT JSON testcases | UAT JSON testcases
| What will you do today? | Debugging and the implementation of our additional function | Debugging and the implementation of our additional function | Debugging and the implementation of our additional function | Not a working day | UAT JSON testcases | UAT JSON testcases | UAT JSON testcases
| Do you have any obstacles? | - | - | - | - | - | - | -
Wang Piao | What did you do yesterday? | Debugging bugs caught during UAT | Debugging and the implementation of our additional function | Debugging and the implementation of our additional function | Debugging and the implementation of our additional function | Not a working day | UAT JSON testcases | UAT JSON testcases
| What will you work on today? | Debugging and the implementation of our additional function | Debugging and the implementation of our additional function | Debugging and the implementation of our additional function | Not a working day | UAT JSON testcases | UAT JSON testcases | UAT JSON testcases
| Do you have any obstacles? | - | - | - | - | - | - | -
Francine | What did you do yesterday? | Debugging bugs caught during UAT | Debugging and the implementation of our additional function | Debugging and the implementation of our additional function | Debugging and the implementation of our additional function | Not a working day | UAT JSON testcases | UAT JSON testcases
| What will you work on today? | Debugging and the implementation of our additional function | Debugging and the implementation of our additional function | Debugging and the implementation of our additional function | Not a working day | UAT JSON testcases | UAT JSON testcases | UAT JSON testcases
| Do you have any obstacles? | - | - | - | - | - | - | -
Risa | What did you do yesterday? | Debugging bugs caught during UAT | Debugging and the implementation of our additional function | Debugging and the implementation of our additional function | Debugging and the implementation of our additional function | Not a working day | UAT JSON testcases | UAT JSON testcases
| What will you work on today? | Fixing bug metric for new bugs caught | Debugging and the implementation of our additional function | Debugging and the implementation of our additional function | Not a working day | UAT JSON testcases | UAT JSON testcases | UAT JSON testcases
| Do you have any obstacles? | - | - | - | - | - | - | -
Minh | What did you do yesterday? | Debugging bugs caught during UAT | Debugging and the implementation of our additional function | Debugging and the implementation of our additional function | Debugging and the implementation of our additional function | Not a working day | UAT JSON testcases | UAT JSON testcases
| What will you work on today? | Debugging and the implementation of our additional function | Debugging and the implementation of our additional function | Debugging and the implementation of our additional function | Not a working day | UAT JSON testcases | UAT JSON testcases | UAT JSON testcases
| Do you have any obstacles? | - | - | - | - | - | - | -

## Week11
| Question | Week 11: 28/10/2019 to 3/11/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Eugene | What did you do yesterday? | Preparation for UAT | Preparation for UAT | Not a working day | Testing and Debugging | Testing and Debugging | Testing and Debugging | UAT
| What will you do today? | Preparation for UAT | Not a working day | Testing and Debugging | Testing and Debugging | Testing and Debugging | UAT | Debugging bugs caught during UAT
| Do you have any obstacles? | - | - | - | - | - | - | -
Wang Piao | What did you do yesterday? | Preparation for UAT | Preparation for UAT | Not a working day | Testing and Debugging | Testing and Debugging | Testing and Debugging | UAT
| What will you work on today? | Preparation for UAT | Not a working day | Testing and Debugging | Testing and Debugging | Testing and Debugging | UAT | Debugging bugs caught during UAT
| Do you have any obstacles? | - | - | - | - | - | - | -
Francine | What did you do yesterday? | Preparation for UAT | Preparation for UAT | Not a working day | Testing and Debugging | Testing and Debugging | Testing and Debugging | UAT
| What will you work on today? | Preparation for UAT | Not a working day | Testing and Debugging | Testing and Debugging | Testing and Debugging | UAT | Debugging bugs caught during UAT
| Do you have any obstacles? | - | - | - | - | - | - | -
Risa | What did you do yesterday? | Preparation for UAT | Preparation for UAT | Not a working day | Testing and Debugging | Testing and Debugging | Testing and Debugging | UAT
| What will you work on today? | Preparation for UAT | Not a working day | Testing and Debugging | Testing and Debugging | Testing and Debugging | UAT | Debugging bugs caught during UAT
| Do you have any obstacles? | - | - | - | - | - | - | -
Minh | What did you do yesterday? | Preparation for UAT | Preparation for UAT | Not a working day | Testing and Debugging | Testing and Debugging | Testing and Debugging | UAT
| What will you work on today? | Preparation for UAT | Not a working day | Testing and Debugging | Testing and Debugging | Testing and Debugging | UAT | Debugging bugs caught during UAT
| Do you have any obstacles? | - | - | - | - | - | - | -

## Week10
| Question | Week 10: 21/10/2019 to 27/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Eugene | What did you do yesterday? | round 2 clearing logic | Testing out Testcases | Integrating JSON | Testing out Testcases | Debugging existing code | Debugging existing code | Debugging existing code
| What will you do today? | Testing out Testcases | Integrating JSON | Testing out Testcases | Debugging existing code | Debugging existing code | Debugging existing code | Preparation for UAT
| Do you have any obstacles? | - | - | - | - | - | - | -
Wang Piao | What did you do yesterday? | round 2 clearing logic | Testing out Testcases | Integrating JSON | Testing out Testcases | Debugging existing code | Debugging existing code | Schedule update and revise
| What will you work on today? | Testing out Testcases | Integrating JSON | Testing out Testcases | Debugging existing code | Debugging existing code | Schedule update and revise | Preparation for UAT
| Do you have any obstacles? | - | - | - | - | - | - | -
Francine | What did you do yesterday? | Drop and Dump Section | Debugging Existing Code | Round 2 Clearing logic (bidding functions) | Testing out testcases | Debugging existing code | Round 2 Clearing logic (bidding functions) | Round 2 Clearing logic (bidding functions)
| What will you work on today? | Debugging Existing Code | Round 2 Clearing logic (bidding functions) | Testing out Testcases | Debugging existing code | Round 2 Clearing logic (bidding functions) | Round 2 Clearing logic (bidding functions) | Preparation for UAT
| Do you have any obstacles? | - | - | - | - | - | - | -
Risa | What did you do yesterday? | testcases for json checker | Testing out Testcases | Integrating JSON | Testing out Testcases | Debugging existing code | Debugging existing code | Debugging existing code
| What will you work on today? | Testing out Testcases | Integrating JSON | Testing out Testcases | Debugging existing code | Debugging existing code | Debugging existing code | Preparation for UAT
| Do you have any obstacles? | - | - | - | - | - | - | -
Minh | What did you do yesterday? | Drop and Dump Section | Debugging Existing Code | Round 2 Clearing logic (bidding functions) | Testing out testcases | Debugging existing code | Round 2 Clearing logic (bidding functions) | Round 2 Clearing logic (bidding functions)
| What will you work on today? | Debugging Existing Code | Round 2 Clearing logic (bidding functions) | Testing out testcases | Debugging existing code | Round 2 Clearing logic (bidding functions) | Round 2 Clearing logic (bidding functions) | Preparation for UAT
| Do you have any obstacles? | - | - | - | - | - | - | -

## Week9
| Question | Week 9: 14/10/2019 to 20/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Eugene | What did you do yesterday? | Test and debugging | Prepare for review | JSON data dump | Round 2 Bidding | Not a working day | JSON for Stop Start Round | JSON for data dumps
| What will you do today? | Prepare for review | JSON data dump | Round 2 Bidding | Not a working day | JSON for Stop Start Round | JSON for data dumps | round 2 clearing logic
| Do you have any obstacles? | - | - | - | - | - | - | -
Wang Piao | What did you do yesterday? | Test and debugging | Prepare for review | Review schedule | Review schedule | Not a working day | Schedule adjustment | JSON for data dumps
| What will you work on today? | Prepare for review | Review schedule | Review schedule and critical path | Not a working day | Schedule adjustment | JSON for data dumps | round 2 clearing logic
| Do you have any obstacles? | - | - | - | - | - | - | -
Francine | What did you do yesterday? | Test and debugging | Prepare for review | Update bid function | JSON bid functions | Not a working day | Clearing logic 2 | test and debugging
| What will you work on today? | Prepare for review | Update bid function | JSON bid functions | Not a working day | Clearing logic 2 | test and debugging | Drop and Dump Section
| Do you have any obstacles? | - | - | - | - | - | - | -
Risa | What did you do yesterday? | Test and debugging | Prepare for review | JSON data dump | Round 2 Bidding | Not a working day | JSON for Stop Start Round | JSON for data dumps
| What will you work on today? | Prepare for review | JSON data dump | Round 2 Bidding | Not a working day | JSON for Stop Start Round | JSON for data dumps | testcases for json checker
| Do you have any obstacles? | - | - | - | - | - | - | -
Minh | What did you do yesterday? | Test and debugging | Prepare for review | Update bid function | JSON bid functions | Not a working day | Clearing logic 2 | testcases for json checker
| What will you work on today? | Prepare for review | Update bid function | JSON bid functions | Not a working day | Clearing logic 2 | testcases for json checker | Drop and Dump Section
| Do you have any obstacles? | - | - | - | - | - | - | -

## Week 8
Person | Question | Week: 30/09/2019 to 06/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Eugene | What did you do yesterday? | Project meeting | Not a working day | Test Cases for Bid Clearing | Testing out Testcases | Update and Drop Bid | Weekly meeting | Bid result overview
| What will you do today? | Not a working day | Test Cases for Bid Clearing | Testing out Testcases | Update and Drop Bid | Weekly meeting | Bid result overview | Testing and Debugging
| Do you have any obstacles? | - | - | - | - | - | - | -
Wang Piao | What did you do yesterday? | Project meeting | Not a working day | Test Cases for Bid Clearing | Testing out Testcases | Update and Drop Bid | Weekly meeting | Modify test cases for bootstrap
| What will you work on today? | Not a working day | Test Cases for Bid Clearing | Testing out Testcases | Update and Drop Bid | Weekly meeting | Modify test cases for bootstrap | Testing and Debugging
| Do you have any obstacles? | - | - | - | - | - | - | -
Francine | What did you do yesterday? | Project meeting | Not a working day | Test Cases for Bid Clearing | Bid validation | Bid Validation | Weekly meeting | Drop Section for Round 1
| What will you work on today? | Not a working day | Test Cases for Bid Clearing | Bid validation | Bid validation | Weekly meeting | Drop Section for Round 1 | Testing and Debugging
| Do you have any obstacles? | - | - | - | - | - | - | -
Risa | What did you do yesterday? | Project meeting | Not a working day | Test Cases for Bid Clearing | Bid validation | Bid Validation | Weekly meeting | Modify test cases for bootstrap
| What will you work on today? | Not a working day | Test Cases for Bid Clearing | Bid validation | Bid validation | Weekly meeting | Modify test cases for bootstrap | Testing and Debugging
| Do you have any obstacles? | - | - | - | - | - | - | -
Minh | What did you do yesterday? | Project meeting | Not a working day | Test Cases for Bid Clearing | Modify critical path | Check Update and Drop Bid function | Weekly meeting | Slides for Week 9 presentation
| What will you work on today? | Not a working day | Test Cases for Bid Clearing | Modify critical path | Check update and drop bid function | Weekly meeting | Slides for Week 9 presentation | Testing and Debugging
| Do you have any obstacles? | - | - | - | - | - | - | -

## Week 7
Person | Question | Week: 30/09/2019 to 06/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Eugene | What did you do yesterday? | Presentation Slides | PM Review | Student Login and Bidding | Student Login and Bidding | Clearing logic planing | Clearing Loggic | Clearing logic
| What will you do today? | Preparation for pm review | Student Login and Bidding | Student Login and Bidding | Clearing Logic Planning | Clearing Logic Planning | Clearing Logic | Project meeting
| Do you have any obstacles? | - | - | - | - | - | - | -
Wang Piao | What did you do yesterday? | Presentation Slides | Preparation for pm review | Student Login and Bidding | Student Login and Bidding | Student Login and Bidding | Student Login and Bidding | Round 1 Clearing Logic
| What will you work on today? | Preparation for pm review | Student Login and Bidding | Student Login and Bidding | Student Login and Bidding | Student Login and Bidding | Round 1 Clearing Logic | Project meeting
| Do you have any obstacles? | - | - | - | - |  | - | -
Francine | What did you do yesterday? | Presentation Slides | Preparation for pm review | testing and debugging | pair programming meeting | student homepage and bidding form | student homepage and bidding forms | student hompage and bidding forms
| What will you work on today? | Preparation for pm review | Testing and debugging | pair programming meeting | student homepage and bidding form | student homepage and bidding form | student homepage and bidding forms | Project meeting
| Do you have any obstacles? | - | Errors with insertion of data on Macintosh | - | - | - | - | -
Risa | What did you do yesterday? | Presentation Slides | Preparation for pm review | Student Login and Bidding | pair programming meeting | student homepage and bidding form | student homepage and bidding form | student hompage and bidding forms
| What will you work on today? | Preparation for pm review | Student Login and Bidding | pair programming meeting | student homepage and bidding form | student homepage and bidding form | student homepage and bidding form | Project meeting
| Do you have any obstacles? |  | - |  | - | - | - | -
Minh | What did you do yesterday? | Presentation Slides | PM Review | update time stamp for iter 2 | weekly meeting summary | not a working day | Finalize bid clearing logic | calculate slacks and critical path
| What will you work on today? | Preparation for pm review | Update time stamp for iter 2 schedule | Weekly meeting summary | not a working day | Finalize bid clearing logic | calculate slacks and critical path | Project meeting
| Do you have any obstacles? | - | - | - | - | - | - | -

## Week 6
Person | Question | Week: 23/09/2019 to 29/09/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Eugene | What did you do yesterday? | Looking through work done in bootstrap | Progress Brief | Not a working day | Weekly Meeting | Revise schedule | Come up with test cases | Testing and debugging
| What will you do today? | Progress Brief | Not a working day | Weekly Meeting | Revise schedule | Come up with test cases | Testing and debugging | Presentation Slides
| Do you have any obstacles? |  | - | - | - |  | Coming up with test cases for finge cases | -
Wang Piao | What did you do yesterday? | Validate csv | validate csv | Not a working day | Weekly Meeting | validate CSV | not a working day | Testing and debugging
| What will you work on today? | Validate csv | not a working day | Weekly Meeting | validate CSV | not a working day | Testing and debugging | making presentation Slides
| Do you have any obstacles? | - | - | - | - | - | - | completing the slides
Francine | What did you do yesterday? | Validate csv | validate csv | Not a working day | weekly meeting | validate csv | not a working day | test and debugging
| What will you work on today? | Validate csv | not a working day | Weekly Meeting | validate CSV | not a working day | Testing and debugging | test and debugging
| Do you have any obstacles? | - | - | - | - |  | - | -
Risa | What did you do yesterday? | Validate CSV | Validate CSV | Not a working day | Weekly Meeting | validate CSV | not a working day | Testing and debugging
| What will you work on today? | Validate CSV | not a working day | Weekly Meeting | validate CSV | not a working day | Testing and debugging | Presentation Slides
| Do you have any obstacles? | - | - | - | - | - | - | -
Minh | What did you do yesterday? | validate CSV | validate CSV | Not a working day | Weekly Meeting | validate csv | not a working day | Testing and debugging
| What will you work on today? | validate CSV | not a working day | Weekly Meeting | validate CSV | not a working day | Testing and debugging | work on presentation slides
| Do you have any obstacles? | - | - | - | - | - | - | -

## Week 5
Person | Question | Week: 16/09/2019 to 22/09/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Eugene | What did you do yesterday? | Not a working day | Planning what classes/daos are required | Not a working day | Excel planning for schedule | Calculate slack and critical path | Prepare for meeting on Sat | Team update and progess brief
| What will you do today? | Working on bootstrap process | Not a working day | Re-format task sheet and schedule | Calculate slack and critical path | Prepare for meeting on Sat | Team update and progess brief | Looking through work done in bootstrap
| Do you have any obstacles? | Need to plan class daos to integrate clearing of table | - | - | - | - | - | Interpreting Regex
Wang Piao | What did you do yesterday? | php revision | iteration planning | Not a working day | Excel planning | Work on Login Form | Classes and DAOs | Bootstrap initiation
| What will you work on today? | iteration planning | Not a working day | Re-format task sheet and schedule | Critical path design | Classes and DAOs | Bootstrap initiation | Validate CSV
| Do you have any obstacles? | assigning different tasks to members | - | - | - | - | - | -
Francine | What did you do yesterday? | Not working day | working on validation for bootstrap files | working on validation for bootstrap files | Excel planning | Work on login form | Classes and DAOs | Bootstrap initiation
| What will you work on today? | Working on validation for bootstrap files | working on validation for bootstrap files | Re-format task sheet and schedule | Work on Login Form | Classes and DAOs | Bootstrap initiation | Validate CSV
| Do you have any obstacles? | - | - | - | - | - | - | -
Risa | What did you do yesterday? | Bootstrap revision | Setting up the database | Not a working day | Excel planning | Bid Class and Bootstrap form | Classes and DAOs | Classes and DAOs
| What will you work on today? | Setting up the database | Not a working day | Re-format task sheet and schedule | Bid Class and Bootstrap form | Classes and DAOs | Classes and DAOs | Validate CSV
| Do you have any obstacles? | - |  | - | - | - | - | -
Minh | What did you do yesterday? | Bootstrap revision | finalize bootstrap process | Not a working day | Excel planning | Prepare for Week 7 presentation | Prepare for saturday meeting | Authentication.php
| What will you work on today? | finalize bootstrap process | Not a working day | Re-format task sheet and schedule | slides for presentation | Prepare for Sat meeting | authentication.php | Validate CSV
| Do you have any obstacles? | need to successfully deliver error messages | - | - | - | - | - | -

## Week 4
Person | Question | Week: 09/09/2019 to 15/09/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Eugene | What did you do yesterday? | Not a working day | Do login page and start bootstrap function | Not a working day | Continuing the bootstrap function | Not a working day | Work on validation for bootstrapped files | Work on validation for bootstrapped files
| What will you do today? | Do login page and start bootstrapping function | Not a working day | Continue bootstrap function | Not a working day | Work on validation for bootstrapped files | Work on validation for bootstrapped files | Not a working day
| Do you have any obstacles? | Bootstrapping process is taught during class so need time to look through first | - | Thinking about what other functions/information the admin needs | - | Need to add additional data in csv to check for validation success | - | Not a working day
Wang Piao | What did you do yesterday? | Not working day | Trello and gantt chart planning | Not working day | Trello planning | Not a working day | Not a working day | Php revision
| What will you work on today? | Trello planning | Not working day | Completing gantt chart planning on trello | Not a working day | Not a working day | Php revision | Php revision
| Do you have any obstacles? | Designing Gantt chart for the team | Not working day | - | - | - | recap php concepts | -
Francine | What did you do yesterday? | Not a working day | Help to design the Login page for administrator | Bootstrap function | Not a working day | First phase of bootstrap function | Not working day | Work on validation for bootstrapped files
| What will you work on today? | Login page for administrator | Start looking into bootstrap function for bidding | Not a working day | Work on the first phase of the bootstrap function - validating csv files | Not a working day | Work on validation for bootstrapped files | Not a working day
| Do you have any obstacles? | Bootstrapping process is taught during class so need time to look through first | - | - | Have to clarify some queries regarding validation on elearn | - | - | -
Risa | What did you do yesterday? | Not a working day | Trello Planning | Gantt Chart arranging | Presentation planning | Not a working day | Not a working day | Flow of validation
| What will you work on today? | Trello Planning | Gantt Chart arranging | Presentation planning | Not a working day | Not a working day | Flow of validation | Bootstrap revision
| Do you have any obstacles? | estimating the appropriate time for each iteration.with the buffer time included | Arranging the Gantt Chart in the most optimal way that is easy to decipher at a glance | - | - | -
Minh | What did you do yesterday? | Not a working day | learnt how to truncate the data | Not a working day | research on bootstraps | Not a working day | UserDAO and User Class | not a working day
| What will you work on today? | Details on bootstraps | Not a working day | research on bootstraps and bidding logic | Not a working day | work on userDAO and user class | not a working day | work on bootstrap csv to sql
| Do you have any obstacles? | bidding logic process | move data from csv to sql database | what is the common errors in the bootstrap process | - | no sql database beforehand | - | -